## Sheet1
Covenant United Methodist Church Prayer Garden
Appendix 3 |  | PROPOSED |  | ACTUAL
Phase | Task | Start Date | Finish Date | Start Date | Finish Date | Man Hours | Resource
Project Definition
| Preliminary write up/ design |  |  |  |  | 2 | Jordan
| Project Review with CUMC Trustees |  |  |  | 2014-03-12 | 1 | Jordan, Trustees
| Trustees Approval |  |  |  |  | 1 | Jordan, Trustees
| Open questions - resubmitted to trustees |  |  |  |  | 2 | Jordan
Project Write up
| Project Write up - Rev 0 |  |  |  |  | 8 | Jordan
| Project Write up review #1 |  |  |  |  | 2 | Jordan, Troop 220
| Project Write up - Rev 1 |  |  | 2014-09-12 | 2014-09-17 | 4 | Jordan
| Project Write up review #2 |  |  | 2014-10-16 | 2014-10-16 | 4 | Jordan, parents, Troop 220
| Project Write up - Rev 2 |  |  | 2014-12-17 | 2014-12-19 | 2 | Jordan
| Project Write Final Review |  |  | 2015-02-07 | 2015-02-07 | 4 | Jordan, parents, Troop 220
| Project Write up Final |  |  |  |  | 1 | Jordan
Approvals
| CUMC Trustees final approval |  |  |  |  | 1 | Jordan, Trustees
| Troop 220 approval |  |  |  |  | 1 | Mr Kesner
| Southwest Council approval |  |  |  |  | 1
Project Funding
| Scout Account funds - $400 |  |  |  |  | 0 | Jordan
| Seek Donations (Family) |  |  |  |  | 2 | Jordan
Materials
| Seek donations (Lowes, Home Depot, Duke City RediMix, others) |  |  |  |  | 2 | Jordan
| Define sources/funding |  |  |  |  | 1 | Jordan
| Obtain materials |  |  |  |  | 3 | Jordan, family
Supplies
| Seek donations (Walmart, Smiths, Family, Chic Fil-A) |  |  |  |  | 2 | Jordan
| Define sources/funding |  |  |  |  | 1 | Jordan
| Obtain Supplies |  |  |  |  | 3 | Jordan, family
Communication
| CUMC approval of work dates | [5 empty] | Pastor Vernon
| Troop 220 Approval of work dates (Nov 8, 11, 15) | [5 empty] | Scout Master/Committee
| Announce work dates at Scout meeting - sign up sheet | [5 empty] | Jordan
| Notify Family of work dates | [5 empty] | Jordan
| Notify band friends of work dates - hang flier | [5 empty] | Jordan
| Work day #2 reminder - sign up sheet | [5 empty] | Jordan
| Work day #2 reminder - email, phone calls | [5 empty] | Jordan
| Work day #3 reminder - sign up sheet | [5 empty] | Jordan
| Work day #3 reminder - email, phone calls | [5 empty] | Jordan
| Work day #4 reminder - sign up sheet | [5 empty] | Jordan
| Work day #4 reminder - email, phone calls | [5 empty] | Jordan
Build Benches (Day 1)
| Hold Safety Talk | 2015-02-21 | 2015-02-21
| Use Bench Drawing for dimension information | 2015-02-21 | 2015-02-21
| Cut 4x4 Steel Tube (57" length) | 2015-02-21 | 2015-02-21 |  |  | 1 | Jordan, dad
| Remove Sharp edges from cutting operation | 2015-02-21 | 2015-02-21 |  |  | 0.5 | Jordan, dad
| Drill holes in 4x4 tubes for 1/2" and 1/4" bolts | 2015-02-21 | 2015-02-22 |  |  | 1 | Jordan, dad
| Remove dirt, oil, rust and loose paint from 4x4 tube | 2015-02-21 | 2015-02-22 |  |  | 0.5 | Jordan, dad
| Prime steel tubes | 2015-02-21 | 2015-02-22 |  |  | 1 | Jordan, dad
| Cut 2x4 Redwood bench boards | 2015-02-21 | 2015-02-22 |  |  | 1 | Jordan, dad
| Route ends of cut boards | 2015-02-21 | 2015-02-22 |  |  | 0.5 | Jordan, dad
| Drill holes in boards for bolts and screws | 2015-02-21 | 2015-02-22 |  |  | 0.5 | Jordan, dad
| Sand boards | 2015-02-21 | 2015-02-22 |  |  | 1 | Jordan, dad
| Seal/stain redwood boards | 2015-02-21 | 2015-02-22 |  |  | 1 | Jordan, dad
| Bolt seat mounting board to legs - 1/2" bolts | 2015-02-21 | 2015-02-22 |  |  | 1 | Jordan, dad
| Bolt back rest mounting boards to legs - 1/4" bolts | 2015-02-21 | 2015-02-22 |  |  | 1 | Jordan, dad
| Screw bench boards to seat supports - 2" screws | 2015-02-21 | 2015-02-22 |  |  | 2 | Jordan, dad
| Screw bench back rest boards to mounting boards - 2" screws | 2015-02-21 | 2015-02-22 |  |  | 2 | Jordan, dad
| Screw top 2x8 cap on bench | 2015-02-21 | 2015-02-22 |  |  | 0.25 | Jordan, dad
| Screw front 2x4 support on bench | 2015-02-21 | 2015-02-22 |  |  | 0.25 | Jordan, dad
| Clean up | 2015-02-21 | 2015-02-22 |  |  | 0.5 | Jordan
Prep For Day 2
| Cut masonite into 3-1/2" strips | 2015-04-11 | 2015-04-11 |  |  |  | Jordan, dad
| Identify 2x4's for concrete forms | 2015-04-11 | 2015-04-11 |  |  |  | Jordan, dad
| Gather stakes | 2015-04-11 | 2015-04-11 |  |  |  | Jordan, dad
| Load tools, supplies and materials into truck | 2015-04-11 | 2015-04-11 |  |  |  | Jordan, dad
|  | 2015-04-11 | 2015-04-11
Work Site Preparation (Day 2)
| Hold Safety Talk | 2015-04-11 | 2015-04-11 |  |  |  | Jordan
| Discuss Plan for the day | 2015-04-11 | 2015-04-11 |  |  |  | Jordan
| Assign work crews for various tasks | 2015-04-11 | 2015-04-11 |  |  |  | Jordan
| Dirt leveling and relocation | 2015-04-11 | 2015-04-11 |  |  |  | 2 adults, 8 scouts
| Layout patio location | 2015-04-11 | 2015-04-11 |  |  |  | Jordan, 2 adults, 2 older scouts
| Install 2x4 forms for patio - level - stake and screw | 2015-04-11 | 2015-04-11 |  |  |  | 2 adults, 4 older scouts
| Back fill dirt against forms - adds support & prevents concrete leaks | 2015-04-11 | 2015-04-11 |  |  |  | 2 scouts
| Layout hole locations for bench legs (6) per drawing | 2015-04-11 | 2015-04-11 |  |  |  | Jordan, 1 adult
| Dig holes to 24" depth | 2015-04-11 | 2015-04-11 |  |  |  | 1 adult, 6 scouts
| Position bench with legs in the holes | 2015-04-11 | 2015-04-11 |  |  |  | Jordan, 2 adults, 2 older scouts
| Brace benches so they don't move and are square | 2015-04-11 | 2015-04-11 |  |  |  | Jordan, 2 adults, 2 older scouts
| Mix QuickCrete | 2015-04-11 | 2015-04-11 |  |  |  | 4 scouts
| Pour one 80# bag of mixed concrete into each hole | 2015-04-11 | 2015-04-11 |  |  |  | 1 adult, 2 scouts
| Post warning sign - not to set on benches | 2015-04-11 | 2015-04-11 |  |  |  | Jordan
| Wash tools used for concrete before concrete hardens on them | 2015-04-11 | 2015-04-11 |  |  |  | 4 scouts
| Thank everyone for coming | 2015-04-11 | 2015-04-11 |  |  |  | Jordan
| Take Pictures | 2015-04-11 | 2015-04-11 |  |  |  | Jordan
| Clean up | 2015-04-11 | 2015-04-11 |  |  |  | Everyone
Prep For Day 3
| Call Duke City RediMix to confirm truck delivery time | 2015-04-25 | 2015-04-25 |  |  |  | Jordan
| Load tools, materials and supplies in truck | 2015-04-25 | 2015-04-25 |  |  |  | Jordan, dad
|  | 2015-04-25 | 2015-04-25
Concrete Pour (Day 3)
| Hold Safety Talk | 2015-04-25 | 2015-04-25 |  |  |  | Jordan
| Discuss Plan for the day | 2015-04-25 | 2015-04-25 |  |  |  | Jordan
| Assign work crews for various tasks | 2015-04-25 | 2015-04-25 |  |  |  | Jordan
| Layout curved sidewalk | 2015-04-25 | 2015-04-25 |  |  |  | Jordan, 2 adults, 2 older scouts
| Install masonite board - stake and screw | 2015-04-25 | 2015-04-25 |  |  |  | 2 adults, 4 older scouts
| Back fill dirt against forms - adds support & prevents concrete leaks | 2015-04-25 | 2015-04-25 |  |  |  | 2 scouts
| Install fiber board for expansion joints | 2015-04-25 | 2015-04-25 |  |  |  | 2 adults
| Premoisten soil in patio and sidewalk area | 2015-04-25 | 2015-04-25 |  |  |  | 1 scout
| Concrete arrives - drops his shoot, starts offloading concrete | 2015-04-25 | 2015-04-25 |  |  |  | concrete driver
| Pour concrete for patio first - screed starting at west end - moving east | 2015-04-25 | 2015-04-25 |  |  |  | 3 adults, 2 older scouts
| Pour concrete for side walk, start at patio - screed moving north | 2015-04-25 | 2015-04-25 |  |  |  | 3 adults, 2 older scouts
| Save one wheelbarrow of extra concrete to fill low spots | 2015-04-25 | 2015-04-25 |  |  |  | 1 older scout
| Vibrate forms to provide clean (void free) edge | 2015-04-25 | 2015-04-25 |  |  |  | 1 older scout
| Bull Float patio - add concrete in any low spots | 2015-04-25 | 2015-04-25 |  |  |  | expert concrete finisher
| Allow concrete to set up | 2015-04-25 | 2015-04-25 |  |  |  | break
| Edge entire patio, sidewalk and control joints | 2015-04-25 | 2015-04-25 |  |  |  | expert concrete finisher
| Add light broom finish to sidewalk | 2015-04-25 | 2015-04-25 |  |  |  | expert concrete finisher
| Wash tools used for concrete before concrete hardens on them | 2015-04-25 | 2015-04-25 |  |  |  | 3 scouts
| Take pictures | 2015-04-25 | 2015-04-25 |  |  |  | Jordan
| Thank everyone for coming | 2015-04-25 | 2015-04-25 |  |  |  | Jordan
| Clean up | 2015-04-25 | 2015-04-25 |  |  |  | Everyone
| Cut control joints in pation | 2015-04-25 | 2015-04-25 |  |  |  | Jordan, dad
Prep For Day 4
| Buy Flowers , gravel and potting soil | 2015-05-02 | 2015-05-02 |  |  |  | Jordan, family
| Load tools, materials and supplies in truck | 2015-05-02 | 2015-05-02 |  |  |  | Jordan, dad
|  | 2015-05-02 | 2015-05-02
Final Site Work (Day 4)
| Hold Safety Talk | 2015-05-02 | 2015-05-02 |  |  |  | Jordan
| Discuss Plan for the day | 2015-05-02 | 2015-05-02 |  |  |  | Jordan
| Assign work crews for various tasks | 2015-05-02 | 2015-05-02 |  |  |  | Jordan
| Remove forms from patio - save stakes and 2x4's | 2015-05-02 | 2015-05-02 |  |  |  | 1 adult, 3 scouts
| Remove forms from sidewalk - save stakes, trash masonite | 2015-05-02 | 2015-05-02 |  |  |  | 1 adult, 3 scouts
| Clean any concrete splatter on benches | 2015-05-02 | 2015-05-02 |  |  |  | 2 scouts
| Touch up any scratches on bench legs | 2015-05-02 | 2015-05-02 |  |  |  | 1 scout
| Touch up any bare spots on redwood | 2015-05-02 | 2015-05-02 |  |  |  | 1 scout
| Add 4" of gravel to 3 flower pots | 2015-05-02 | 2015-05-02 |  |  |  | 2 scouts
| Fill remainder with potting soil - about 3" from top of pot | 2015-05-02 | 2015-05-02 |  |  |  | 2 scouts
| Flowers to be installed in spring | 2015-05-02 | 2015-05-02 |  |  |  | Jordan
| Take Pictures | 2015-05-02 | 2015-05-02 |  |  |  | Jordan
| Thank everyone for coming | 2015-05-02 | 2015-05-02 |  |  |  | Jordan
| Clean up | 2015-05-02 | 2015-05-02 |  |  |  | Everyone
TOTAL LABOR HOURS | [5 empty] | 63